## Sprint 3 - Week 3 (327-
| Epic | User Story | Status | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | Total Hours
Andre |  |  |  | Terminal when displaying errors shows 2 errors now, instead of the initial 4 I was dealing with. React-Gesture continues to be an issue, and the modules for dependencies seem to be missing still. Referencing REACT tools for resolving component issues in the Developer Tools in Chrome displays more errors for accurate troubleshooting. Attempted Yarn installs over new Node_module installations for potential resolutions to dependencies, as YARN/EXPO can resovle the conflicts. Changed Dependeny requirements listed in package-json for potential resolutions, conflicting dependencies were affected. (2 hours) | Referenced REACT API for hints to resolving running REACT repos, essentially this repo is all JavaScript. Backend_Worker and Storage components work fully, mongodb connection established as well successfully. Frontend/Src is the reamining component that will not load the webpage for PeerPresents. Storage needed the api files for authentication purposes that were needed to keep a consistent connection. Backend_Worker needed no troubleshooting. MongoDB ran after updating the versions to the latest available model. (2.5 hours) | Met with Elliott in-person and resolved issues related to Linux setup and loading/displaying datasets in the app. Encountered errors in dev tools console related to the gesture-handler, and in terminal running app errors related to react-native-web appeared. Spent some time troubleshooting and comparing dependency versions. Fix included steps 1) npm install react-native-web globally, 2) npm install react-native-web@0.11.7 in /frontend/src using --legacy-peer-deps and --no-save flags to preserve dependency tree in case we needed to go back, 3) renamed file extension of createNativeWrapper.js to .jsx, also reviewed a couple of steps to (temporarily) fix window jitter issue, using dev tools and react extensions (1 hour) Discord meeting with the team to prepare for demo day presentation. Chris tried the same fix for rendering datasets that worked for me without success, so we worked together using the same approach that led to that solution. Provided terminal history from yesterday's successful setup, compared dependency tree, identified npm ci command (clean install, with proper flags it can force exact duplication of package-lock tree) as potential fix. (1.5 hours) |  |  |  |  | 7
Chris |  |  |  | Broke frontend and back_end by using "npm update" to update all dependencies to "wanted" versions. worked on fixing that. Fixed what i broke, still can not access data tab.(1.25hrs) + (.25hrs) | continued the data tab saga. met with Julio. worked with Elliot (3.5hrs) | Discord meeting with the team to prepare for demo day presentation. Tried the same fix for rendering datasets that worked for Andre without success, so we worked together using the same approach that led to that solution. Provided terminal history from yesterday's successful setup, compared dependency tree, identified npm ci command (clean install, with proper flags it can force exact duplication of package-lock tree) as potential fix. Continued continued working through the history after our meeting ended. (1.5 hours+3.5hrs) | Sprint Presentation / Team meeting(.5hrs) |  |  |  | 10.5
Elliott | Implement Add Graph Button functionality |  | Add Graph Button Functionality ready for review | Exercise in using React, ReactDOM createElement(), createRoot(), and render() (0.5 hours) | Followed up with team discussion from last night - the dependency tree on my laptop setup is still different to the others', so I looked into the lock files (yarn and package-lock) in frontend as a possible explanation. These files are intended to lock the exact dependency tree installed, and while the versions included in the fa_dev branch I pushed seem to match my current lock files it's simple enough to check into. I have provided both of these files plus my package.json to Andre and Chris, and asked them to try also force clearing their npm cache before trying to re-install node_modules with these files in place. Also mentioned a change I forgot to document and communicate: edited the uri_header value in the backendAPI - it previously referenced the live deployment's uri instead of the localhost:3010/api, so it's possible this has created problems and have communicated this change as well. (1 hour) Tentatively scheduled, planned post-sprint reflection meeting and demo day presentation planning meeting for Wednesday, got some agendas and documents updated, compared our current board with Julio's example (1 hour) Met with Julio and discussed progress, methodology for passing data between components using props and states, approval for collaborative development (in a web sandbox, in-person, or screen sharing), and viability of the lock files approach to resolve dependency issues (1 hour) Worked with Chris to test replacing lock files, clearing npm cache, and trying to reinstall packages while preserving the dependency tree from my environment (0.5 hours) Worked a bit more on Implement Add Graph Button functionality; successful through a custom event and receiving event listener to trigger an addGraph() function in the graphscontainer. This solution is inelegant, but works - will try to clean it up a bit (0.75 hours) Spent the rest of the evening troubleshooting my desktop dev. environment setup; systematically applied all of the potential fixes we've covered, manual installs of dependencies (via npm, yarn, and expo), reading documentation about versions of expo and the deprecated expo-cli tool (SDK 45), docs on native-gesture-handler, and some discussion topics. Changing the file extension for createNativeWrapper.js to .jsx appears to have fixed the problem viewing datasets - this was not required for my laptop, however (1.75 hours) | Transcribed and compiled the notes for our 3/16 client meeting (1 hour) Met with Andre in-person and resolved issues related to Linux setup and loading/displaying datasets in the app. Encountered errors in dev tools console related to the gesture-handler, and in terminal running app errors related to react-native-web appeared. Spent some time troubleshooting and comparing dependency versions. Fix included steps 1) npm install react-native-web globally, 2) npm install react-native-web@0.11.7 in /frontend/src using --legacy-peer-deps and --no-save flags to preserve dependency tree in case we needed to go back, 3) renamed file extension of createNativeWrapper.js to .jsx, also reviewed a couple of steps to (temporarily) fix window jitter issue, using dev tools and react extensions (1 hour) Finished transcription of 3/16 client meeting notes, cleaned up and compiled notes from that day's sprint planning meeting as well, organized deliverables for submission (1 hour) Completed S3 surveys and compiled my STARFISH reflection points for the post-sprint meeting (if this shouldn't apply toward project hours, please subtract from weekly total) (1 hour) Discord meeting with the team to prepare for demo day presentation. Chris tried the same fix for rendering datasets that worked for Andre without success, so we worked together using the same approach that led to that solution. Provided terminal history from yesterday's successful setup, compared dependency tree, identified npm ci command (clean install, with proper flags it can force exact duplication of package-lock tree) as potential fix. (1.5 hours) | Worked on improving Add Graph Button functionality; cleaned up comments and spaghetti code, broke and tested it, committed and pushed branch to demo but it's complete enough to request code review and move forward on a new task. At some point, may need to: overload/use defaults for addGraph() function in order to integrate into the GraphsContainer constructor and able to either update the state with specific graphs (from dataset>sessionlist>graphlist) or default values. Looked into fixing the window jitter bug - it may be related to outdated react packages or CSS sizing/flex-box attributes. Possibly related to react animations. Unable to resolve quickly, and it's not a priority for now. (2 hours) Reviewed, organized, exported all notes and deliverables for S3 submission, screenshots of project board, new branch and updated, formatted README.md file. It will be ready to push with minor update to the MD file once we hold our reflection meeting tonight, export that, timesheet (+ try to format better for excel). Prepared for Demo (additional speaking notes on key React/js/code points) and met with Andre. Observed possible cause for window jitter/flicker - potentially moving the <MainButton> for addGraph outside of the container - will try since it would be a quick and easy fix. Won't be able to work on this project much until next Tuesday (2+ hours) Reflected with the team, we laughed, we cried, we had some good ideas. Took notes, exported remaining docs and will be pushing everything to our GH shortly (0.5 hours) |  |  |  | 14.5

## Sprint 3 - Week 2 (320-326)
| Epic | User Story | Status | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | Total Hours
Andre |  |  |  | VirtualBoxVM (which was used in Linux) is giving me troubles with hard drive storage to allow npm installation on frontend page again. Known methods of partitioning storage has failed, such as "Virtual Size Manager" and "modifyhd/modifymedium". GParted tool which assists with stoage allocation hasn't helped with storage increase.(3 hrs) | Held mid-sprint progress check in class and met with the team, finalized sprint goals. Worked with Chris to resolve errors preventing loading of the Dataset frame, possibly related to modifying AdminNavigation.js code or node package versions/dependencies. Attempted to import working node_modules from frontend, install alternate versions of react and react-native-webview, downgrade global expo-CLI, and override npm installations with flags related to dependencies; compared and traced backward in the console error stack. WIP. We all worked toward different tasks, but agreed on a plan moving forward that allows us to begin development during this sprint. Updating GH Project board TBD, but tasks/goals can be found listed in 3_21_23 Team Meeting Notes. Rescheduled weekly client meeting to Thursday in order to allow time for more progress between meetings (2.5 hours) |  | team meeting; refer to 3_23_23 Team Meeting Notes (1.5 hours) client meeting; refer to 3_23_23 Client Meeting Notes (1.25 hours) | Instead of using Linux, restarted using Ubuntu, along with a bash command to do most of the installations that were required for running the repo. Complications with the frontend'd dependencies were still displated. React-Native-Web refuses to recongize dependency being met, as I've installed the required version and ensured it's being referenced. Something with React-Gesture-Handler is the most likely cause that's prohibiting the Frontend webpage from loading. (3 hrs) |  |  | 9.75
Chris |  |  |  | same as Elliot | Held mid-sprint progress check in class and met with the team, finalized sprint goals. Worked with Chris to resolve errors preventing loading of the Dataset frame, possibly related to modifying AdminNavigation.js code or node package versions/dependencies. Attempted to import working node_modules from frontend, install alternate versions of react and react-native-webview, downgrade global expo-CLI, and override npm installations with flags related to dependencies; compared and traced backward in the console error stack. WIP. We all worked toward different tasks, but agreed on a plan moving forward that allows us to begin development during this sprint. Updating GH Project board TBD, but tasks/goals can be found listed in 3_21_23 Team Meeting Notes. Rescheduled weekly client meeting to Thursday in order to allow time for more progress between meetings (2.5 hours) | studied REACT and its components(2hrs) | team meeting; refer to 3_23_23 Team Meeting Notes (1.5 hours) client meeting; refer to 3_23_23 Client Meeting Notes (1.25 hours) | pulled new branch from Elliot, uploaded node_module in hopes of fixing Data tab error -- no luck.(1hr) | worked on Data tab error (3 hr) | data tab issue. tried updating individual dependencies and worked trough code. not luck read about react and victory bar graphs. rewatched portions of meeting with Julio. (2.5 hrs) | 9.75 hrs
Elliott | Implement Add Graph Button functionality |  | Incomplete | Check-in: I've been terribly busy for the past week, and had no chance to work on the project outside of planned meeting times with the team. Updated to discuss plans before class tomorrow including outlining task proposal, compiling notes from the past sprint planning meeting and Thursday client meeting, intent to test instructor login credentials (0.5 hours) | Reviewed project code and went through the Data WFs to break down the goal into tasks with context from last week's client meetings. Took notes on possible approaches to implementing features: Add Graph, X-Axis Dropdown, Y-Axis Dropdown, Datatype Dropdown, Hover text, and stretch goals for the remaining sprints (2 hours) Held mid-sprint progress check in class and met with the team, finalized sprint goals. Worked with Chris to resolve errors preventing loading of the Dataset frame, possibly related to modifying AdminNavigation.js code or node package versions/dependencies. Attempted to import working node_modules from frontend, install alternate versions of react and react-native-webview, downgrade global expo-CLI, and override npm installations with flags related to dependencies; compared and traced backward in the console error stack. WIP. We all worked toward different tasks, but agreed on a plan moving forward that allows us to begin development during this sprint. Updating GH Project board TBD, but tasks/goals can be found listed in 3_21_23 Team Meeting Notes. Rescheduled weekly client meeting to Thursday in order to allow time for more progress between meetings (2.5 hours) | Checkin with team: to-do list for tomorrow includes updating/transcribing goals & tasks to GH Project Board, get notes documents updated (3x) and agenda for tomorow's team and client meetings, make progress on one of the high priority tasks (coding), and continue sorting out the issues listed yesterday from my end. Should be able to spend most of the day working on these (0.25 hours) Watched a few videos covering props and states, component rendering, and hook usage in react (0.75 hours) | Created kanban board in the PeerPresents repository - read through GH Projects documentation & more about kanban boards and usage. I lacked organizational administrative access (Ludolab) to create a new project in the current system, so this was created as a Classic Project. This is why it took much longer than expected to actually create it despite trying to follow the official github guide on projects. Still need to populate the board with the existing tasks, but that should go more quickly. Lower priority is changing settings - originally created using the basic board template (1 hour) populated board with tasks - temporarily placeholders as notes - need to ask group about creating pull requests/issues (to make them functional cards) and breaking into subtasks (0.75 hours) began work on Implement Add Graph Button functionality; referenced project lucid model diagram for the Graph schema. Will need to run back through some tutorials about react component usage before I'll be able to make real progress. Expect to do the above this evening after meetings, and should have at least limited functionality for adding graphs to the GraphContainer completed today or tomorrow (1 hour) Team meeting; refer to 3_23_23 Team Meeting Notes (1.5 hours) client meeting; refer to 3_23_23 Client Meeting Notes (1.25 hours) Per client advise, I created and pushed 2 branches from my working local /dev -- origin/fa_dev and origin/fa_dev_with_modules --identical except 2x .gitignore files were modifed to include PeerPresents/frontend/src/node_modules/ and should be recommented before pushing any branches based on this one /node_modules/ is too large to upload to github, instead manually download from google drive sprint 3 folder (0.5 hours) | Read through JS documentation on shorthand property naming incl. (generator methods and usage https://developer.mozilla.org/en-US/docs/Web/JavaScript/Reference/Functions/Method_definitions), object initializer (https://developer.mozilla.org/en-US/docs/Web/JavaScript/Reference/Operators/Object_initializer) as part of react tutorial, worked through some examples toward current project goal (1.25 hours) went through my command history from original setup and identified a couple potential global node packages installed. passed that info along during my check-in with team - add graph currently WIP, plans for the weekend. Will continue with this task tomorrow, try to set up dev environment on another computer to see if that helps to sort out any of the current issues, and get our documents up-to-date. (0.5 hours) | looked through mine and julio's npm installs, read through some dependency/dependent lists for what seem to be the relevant packages (expo, expo-cli, react-native, react, react-gesture-handler), checked through my global npm installs to see if any handlers were installed that i was unaware of. Didn't find much of anything, but have advised Chris to try installing expo globally. (0.75 hours) Working through react course's js prerequisites: arrow functions and function definitions/usage, destructuring (basically equivalent to Python unpacking), ..., then finished going through js prereqs • parameter defaults • rest/spread ('...' syntax) • ESModules (import/export) • ternaries • notable array methods • nullish coalescing operator (??) • optional chaining (thing?.property?.example) promises and async/await (need to revisit this one) (2.75 hours) setup course repo, ex: 1 + ec, ex 2 (React.createElement(), .createRoot(), React and ReactDOM) (1.75 hours) setup, on desktop - same error that chris sees. don't hink the solution is commenting out lines in native-gesture-handler, but it does have the same effect as him. (0.75 hours) | Spent today working on add_graph_button_functionality but was unable to finish. Was primarily working with GraphsContainer, Graph, DatasetScreen, and referencing backendAPI & some related components to validate the stored dataset records as well as modify the constructor for GraphsContainer. Currently struggling with which components need to be modified in order to allow new Graphs to be added into a dataset's GraphContainer; I know these need to be passed by a prop into GraphContainer so that it can update its own state, but accomplishing this is more difficult than anticipated because I lack experience. I'm afraid I'll have to spend some additional time learning and practicing a bit on working with props, using the updateState() hook, and structure/interaction between components before I can make progress. My time today was spent working with code or reading documentation related to this code. Have committed my progress, but it's mostly tangential to the task so it will likely be reverted before making any pull request (1.25 hours + 1 hour + 1.75 hours + 0.25 hours) | 22.25

## Sprint 3 - Week 1 (313-319)
| Epic | User Story | Status | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | Total Hours
Andre |  |  |  |  | Met with Dr. Cook to review existing Wireframes and project goals. Will need to schedule a followup with our other client, Julio. Details can be found in 3_13_23 Client Meeting Notes. Scheduled sprint planning meeting for 3/16 (0.75 hours) | Worked with Elliott over Discord to troubleshoot MongoDB config on a fresh linux install (success) and discovered dependency issue possibly related to the linux setup guide(2 hrs). | Misseed meeting due to having to go out of town, group informed and reviewed notes from meeting (30 minutes.) |  |  |  | 3.25 hrs
Chris |  |  |  |  | Met with Dr. Cook to review existing Wireframes and project goals. Will need to schedule a followup with our other client, Julio. Details can be found in 3_13_23 Client Meeting Notes. Scheduled sprint planning meeting for 3/16 (0.75 hours) |  | Held sprint planning meeting with Chris and notes from Andre to discuss goals and strategies to set tasks both for this sprint and the remaining time in the project, go over the project code, looked into implementing graphs. Also met with Julio to go over specific elements of the code related to the components and frames that we'll be using, importing data from the db and passing values through props using React. Gained access to instructor login credentials. (1.75 hours)
Elliott |  |  |  |  | Check-in with team - scheduling sprint 3 planning meeting, setup counsel, expectations for the week, updated timesheet, created Sprint 3 folder in google drive, docs for Client Meeting (.75 hours) Met with Dr. Cook to review existing Wireframes and project goals. Will need to schedule a followup with our other client, Julio. Details can be found in 3_13_23 Client Meeting Notes. Scheduled sprint planning meeting for 3/16 (0.75 hours) | Worked with Andre over Discord to troubleshoot MongoDB config on a fresh linux install (success) and discovered dependency issue possibly related to the linux setup guide; installed versions of packages on my system don't match those I've specified to install (react installed is ver. 7.0.1, advised is ~6.11.x, and dependencies relying on this version are not successfully installing causing errors on page render - need to go over setup again and confirm whether this is an issue for Chris; if it isn't, there shouldn't be a problem moving forward but if there is it's crucial to discover and correct the issue ASAP) (2 hours) | Outlined meeting notes with proposals for this sprint's goals and strategies to set tasks. Compiled an agenda to address during our planning meeting. (2 hours) Held sprint planning meeting with Chris and notes from Andre to discuss goals and strategies to set tasks both for this sprint and the remaining time in the project, go over the project code, looked into implementing graphs. Also met with Julio to go over specific elements of the code related to the components and frames that we'll be using, importing data from the db and passing values through props using React. Gained access to instructor login credentials. (1.75 hours) |  |  |  | 7.25

## Sprint 2 (3) - Spring Break (36
| Epic | User Story | Status | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | Total Hours
Andre | Local Dev Environment Setup |  |  | Focused more onto the Storage component to get MongoDB Setup. MongoDB fails to start, with latest versions or legacy versions noted in README. (1 hour) |  | Able to run Frontend to load webpage with no database connection. Had to run NPM insatllation with node_modules folder being deleted to update versions of dependecies variant to Node. Had to remove components from Frontend as well, which were prohibiting the webpage from displaying within Chrome, such as "react-style-components". (2 hrs) |  |  |  |  | 3 hrs
Chris | Local Dev Environment Setup | [7 empty] | Fixed terminal issues, development environment setup (??? hours) Worked through some storage/backend connection errors and configuration (api_conf.js, ppdb_conf.js) with Elliott over Discord; success! (.5 hours)
Elliott | Local Dev Environment Setup |  |  | Finished the procedural Ubuntu setup guide, "improved" formatting, and made some updates to the unordered notes section (22.04 now officially supported in the guide, added software version info for reference) (1.5 hours) | Read and reviewed JavaScript documentation - closure (developer.mozilla.org/en-US/docs/Web/JavaScript/Closures), template literals (developer.mozilla.org/en-US/docs/Web/JavaScript/Reference/Template_literals), precedence (developer.mozilla.org/en-US/docs/Web/JavaScript/Reference/Operators/Operator_Precedence#table) (1 hour) |  |  |  | Drafted, e-mailed clients & team to coordinate scheduling for next Tuesday's client meeting to discuss wireframes and project goals during S3 (.5 hours) Worked through some storage/backend connection errors and configuration (api_conf.js, ppdb_conf.js) with Chris over Discord; success! (.5 hours) |  | 3.5

## Sprint 2 - Week 3 (227-35)
| Epic | User Story | Status | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | Total Hours
Andre | Local Dev Environment Setup |  |  |  | team meeting - discussed sprint 2 demo /sprint 2 reflections / local setup troubleshooting. (1.5 hrs) Client meeting with Julio. Progress check and plans for over spring break. (.5 hrs) |  | Met with Elliott/Chris to discuss and prepare our S2 presentation for Demo Day (.75 hours) Met in-person with team following demonstrations to complete our S2 reflection meeting (.5 hours) |  |  |  | 3.25
Chris | Local Dev Environment Setup |  |  | terminal "killed" trouleshooting(1hrs) | team meeting - discussed sprint 2 demo /sprint 2 reflections / local setup troubleshooting. (1.5 hrs) Client meeting with Julio. Progress check and plans for over spring break. (.5 hrs) terminal "killed" trouleshooting(1hr) | local enviorment setup (1hr) | Met in-person with team following demonstrations to complete our S2 reflection meeting (.5 hours) |  |  |  | 11.75
Elliott | Local Dev Environment Setup |  |  |  | team meeting - discussed sprint 2 demo /sprint 2 reflections / local setup troubleshooting. (1.5 hrs) Client meeting with Julio. Progress check and plans for over spring break. (.5 hrs) | Individual section S2 Reflection, survey + STARFISH responses (2 hours) Drafting human-readable local development environment setup notes/instructions; WIP (2 hours) | Notes doc based on recommended presentation format and looked into M1 (ARM) compatible Linux installation (Asahi & a community-supported alpha Ubuntu build) with the latter being unnecessary as Chris also has access to other architecture (1 hour) Met with Andre to discuss and prepare our S2 presentation for Demo Day (.75 hours) Met in-person with team following demonstrations to complete our S2 reflection meeting (.5 hours) Updated documents/deliverables, committed and pushed to repo, updated README.md to reflect additional information. worked on formatting - the timesheet looks awful when exported in excel format. included sprint 2 progress notes (1.5 hours) |  | Worked on Linux setup guide - integrating step-by-step documentation with links to resources and comments. WIP (1 hour) |  | 10.75

## Sprint 2 - Week 2 (220-226)
| Epic | User Story | Status | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | Total Hours
Andre | Local Dev Environment Setup |  |  |  | In-class meeting: had mid-sprint progress check. Project plan may change depending on our progress by Sunday 2/26. Continue documenting any changes. Team meeting - made progress in setup related to MongoDB configuration/installation process. (1.5 hours) Client meeting with Julio - changes we've made thus far seem good - see 2_21_23 Client Meeting Notes for more details (.75 hours) |  | Met with Elliott in-person to work on database issues related to Mongo Shell access and troubleshooting configuration steps listed in https://github.com/Ludolab/PeerPresents/blob/master/docs/admin/server_setup_guide.md Shell can be accessed through mongosh (not mongo) and networking info must match defaults or be parameterized providing a specific ip and port number. Regained access without having to reinstall. (.75 hours) |  |  |  | 3
Chris | Local Dev Environment Setup |  |  | Local env. work. Managed to load webpage. (1.5hrs) | In-class meeting: had mid-sprint progress check. Project plan may change depending on our progress by Sunday 2/26. Continue documenting any changes. Team meeting - made progress in setup related to MongoDB configuration/installation process. (1.5 hours) Client meeting with Julio - changes we've made thus far seem good - see 2_21_23 Client Meeting Notes for more details (.75 hours) Additional work on Mongo connection to PeerPresent. (1hr) - (Total 3.25) |  | mongo setup/troubleshoot (1.5hrs) |  | terminal "killed" trouleshooting(2hrs) | terminal "killed" trouleshooting (3.5hrs) | 11.75
Elliott | Local Dev Environment Setup |  |  |  | In-class meeting: had mid-sprint progress check. Project plan may change depending on our progress by Sunday 2/26. Continue documenting any changes. Team meeting - made progress in setup related to MongoDB configuration/installation process. (1.5 hours) Client meeting with Julio - changes we've made thus far seem good - see 2_21_23 Client Meeting Notes for more details (.75 hours) |  | Met with Andre in-person to work on database issues related to Mongo Shell access and troubleshooting configuration steps listed in https://github.com/Ludolab/PeerPresents/blob/master/docs/admin/server_setup_guide.md Shell can be accessed through mongosh (not mongo) and networking info must match defaults or be parameterized providing a specific ip and port number. Regained access without having to reinstall. (.75 hours) | Successful setup? Looked into database migrations (research) and project code related to db (schema, scripted actions, terminal errors when r/w), comparison between firefox, chrome incompatabilities using respective browser dev tools (DOM includes all elements for both, but does not display certain elements at all in FF and does in Chrome), conveying findings to group specifically step to try chrome after downloading, installing, running compass with connection to 127.0.0.1:27017. Modified mongod.conf file and identified workaround to regain access to mongo shell. Tested to confirm that frontend, storage, and worker were functional and performing CRUD actions in database. Documented steps above and relayed information and current status to the team. (2.25 hours + 1 hour + .75 hour) | Compiled questions for Julio regarding setup - looked into some of the code related to mongo and the schema, read through and researched warning/error logs (frontend not displaying all elements properly in Firefox, mostly correct in Chrome; storage doesn't like the data type for some argument somewhere when reading, possibly other CRUD actions but appears to be functional) Awaiting approval for setup (1 hour) Uploaded and updated documents - meeting notes, timesheet, check-in information (.75 hours) Troubleshooting collaboration: researched system commands "killed" issues for M1/homebrew (1 hour) • possibly $PATH incorrect ◦ try modifying .zsh files (.zshrc and/or .zlogin/.zprofile if you can find the /path/to/relevant/locations) • permissions need to be modified /to/some/locations • possibly boot in safe mode to regain access to shell broken shell commands • unfortunately uninstall/reinstall of homebrew and packages installed through brew • caution with sudo? it works differently* on mac? "doesn't provide full access" • homebrew installations use symlinks so $PATH needs to be set correctly Troubleshooting collaboration: mongod service through homebrew - mongo shell specifically (2 hours) • how to kill and restart if brew services isn't working correctly • confirmed installation via most current method https://github.com/mongodb/homebrew-brew (brew tap?) • compared permissions between linux/mac + version for mongod • possibly bypass shell entirely with using mongo compass (gui) • general research in discussions about homebrew + mongodb compatibility | Sunday tasks (1.25 hours) • replied to julio's post about live db access, e-mail for instructor code • tested remote login/access to production db (account creation works, see class data); awaiting e-mail with instructor code and more information about development and database (use production db? copy it locally? seed data?) • looked into installation problems for mongodb (and homebrew in general) on mac and wrote up a bit more in the team discord about the every process/command killed issue and how to proceed: if troubleshooting current installation, more information from error logs and alternatively a fresh, manual install • bookmarked a few relevant resources and offered to share those Sunday cont.'d (3.25 hours) • Continued troubleshooting killed issue with the team; exploring various potential causes and possible solutions: ◦ identified likely cause/series of commands that led up to it by checking logs (through console) and command history (via history -> .zsh_history) to identify copying /usr/bin/* to /usr/local/bin/ and creating a symlink - problem might be ownership of the copied directory and files, or possibly symlink was created in an unintended location ◦ went through $PATH variable and identified a couple of quirks such as duplicate /usr/local/bin and old versions of mongo (though those don't seem likely culprets for killed issue) ◦ Spent time exploring various paths and their contents ◦ Identified key difference between intel and ARM macs which helped to identify /usr/local/ as a potential problem since homebrew installs to /opt/homebrew/ instead in M1+ • Drafted status e-mail requested by client | 14.75

## Sprint 2 - Week 1 (213-219)
Name | Epic | User Story | Status | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | Total Hours
Andre | Local Dev Environment Setup |  |  |  | Team-meeting primarily troubleshooting to get dev environments set up; progress made but still need to sort out starting/connecting back-end server (1.5 hours) Met with Julio from 4:05-4:50 during which we focused on real-time feedback while troubleshooting our collective environment setup and changes/strategies we had employed. More details are contained in the 2/14 notes (0.75 hours) | Backend_Worker successfully running after adjusting dependenices in the apps.js, as well as configuring the versions (1 hour). | Team-meeting. Discussed agenda items (see 2_16_23 Team Meeting Notes); remainder of time spent troubleshooting individual issues with development environment setup. Updated team documents. Exchanged some information with Julio. (1.5 hours) |  | Worked on Backend_Master folder to incorprate with Backend_Worker as Master error reflected what was displayed from Worker folder. (1.5 hours) | Learned the React API to further understand the development/structure of project repo (2 hours). | 6.75
Chris | Local Dev Environment Setup |  |  |  | Team-meeting primarily troubleshooting to get dev environments set up; progress made but still need to sort out starting/connecting back-end server (1.5 hours) Met with Julio from 4:05-4:50 during which we focused on real-time feedback while troubleshooting our collective environment setup and changes/strategies we had employed (50 min). More details are contained in the 2/14 notes (0.75 hours). Having issues still with local setup on computer. Setup on VMware to circumvent possible M1 conflicts (1hr) |  | Team-meeting. Primarily troubleshooting local enviornment issues. (1.5hrs) Continued troubleshooting (1.5hrs) | Downloaded main branch in effort to get local env. working. Frontend would not load / Troubleshoot (1hr) | Continued work on trying to get Master / frontend to load. Compared code from dev and master. Talked to ChatGPT. (2hr) | localhost troubleshooting. reread installation setup. having issues connecting to mongod. website will load but only to blank page still. (2hrs) | 9.75
Elliott | Local Dev Environment Setup |  |  |  | Check-in with the team and housekeeping items - duplicated Figma WFs for modification as Julio directed, compiled questions to ask about connecting to DB (0.5 hours) Pre-meeting collaboration (0.5 hours) Team-meeting primarily troubleshooting to get dev environments set up; progress made but still need to sort out starting/connecting back-end server (1.5 hours) Met with Julio from 4:05-4:50 during which we focused on real-time feedback while troubleshooting our collective environment setup and changes/strategies we had employed. More details are contained in the 2/14 notes (0.75 hours) |  | Team-meeting. Discussed agenda items (see 2_16_23 Team Meeting Notes); remainder of time spent troubleshooting individual issues with development environment setup. Updated team documents. Exchanged some information with Julio. (1.5 hours) Troubleshooting setup continues - compared remote repo branches, compared and attempted to transplant missing directories/files from other working directories (/backend_worker/ contains missing elements referenced by /backend_master/ error logs), researched documentation noted in current error stack traces such as require() and specific modules; attempted fresh setup in master branch (deviates from instructions, unsuccessful - discard changes) (2.5 hours); followed up on Andre's observation, and alongside some questionable and excessive pruning, was successful - more info in Discord checkin (2 hours) | Check-in - formatted notes and thoughts concerning yesterday's progress. May include abbreviated discord logs in sprint deliverables or cite relevant discussions in team meeting notes moving forward. (0.5 hour) Followed Server Setup Guide in PP documentation as suggested in order to confirm local installation of MongoDB is configured properly; WIP (1 hour) |  | Cleaned up local repo as changes were made and confirmed across multiple branches and commits, and formatted my notes documenting troubleshooting steps to improve readability in to receive feedback/clearance from Julio. Also checked in with team regarding our S1 feedback, and updated Team docs, specifically this timesheet, to improve readability per that feedback and 2/16 change that was missed. (.75 hour) | 11.5

## Sprint 1
| Epic | User Story | Status | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19
Andre |  |  |  | Preliminary team meeting: introductions, completed contract (1.5 hours) | First meeting with client + in-class group session (1.5 hours)
Chris |  |  |  | Preliminary team meeting: introductions, completed contract (1.5 hours) | First meeting with client + in-class group session (1.5 hours) | worked on react setup(node), local development setup/troubleshooting same issue with npm install on frontend (3 hrs) | in class coordinating/troubleshooting npm issues (2.5 hrs) |  | Tried to troubleshoot setting up local environment issues (2hrs) | Cont. working on setting up local enviornment(1:45) | local envior. setup troubleshooting. setup project in VM. Client meeting. 3hrs
Elliott |  |  |  | Preliminary team meeting: introductions, completed contract (1.5 hours) | First meeting with client + in-class group session (1.5 hours) | Local Development Environment setup and troubleshooting; ongoing issue with npm install for the frontend, otherwise mostly successful (2.5 hours) | Troubleshooting Dev Environment Setup (Focus was resolving mismatched dependencies), Continued in-class coordinating Sprint 1 deliverables with group (2.0 + 1.5 = 3.5 hours) |  | Troubleshooting dev environment setup. Modified /frontend/src/package.json per notes in the team discord, and was able to start the server locally. Database still refuses connection, but everything seems to be working pending approval for changes made. Communicated the above with team. (1.5 hours)

## Template
| Epic | User Story | Status | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06
Teammate 1 | Register for League | As a player, I can pay with Paypal when I register online | Active | finish task 1 (3 hours) | Finish Task 1, start task 2 & 3 (2 hours) |  | Finish task 2 (1.5 hours) | finish task 3 | attend team meeting (.5 hour)
Teammate 3 | Register for League | As a player, I can pay with Paypal when I register online | Active | [5 empty] | finish task 3 ( 2 hours)
Teammate 2 | Register for League | As a player, I can add league dates to my calendar after I register | Backlog | [6 empty] | start?
Teammate 2 | Register for League | As a league coordinator, I can create a registration survey | Complete | start task 1 | start task 1 (2.5 hours) | finish task 1 (3 hours) | finish task 1 part A (1 hour) |  | finish task 1 part B, attend team meeting (2.5 hours)
Teammate 3 | Register for League | As a captain, I can view all responses to a league signup | Active |  | research how to do task 1 (1.5 hours)

## Blank
| Epic | User Story | Status | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | Total Hours
Andre
Chris
Elliott