## Sprint 2 - Week 1 (213-219)
Name | Epic | User Story | Status | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | Total Hours
Andre | Local Dev Environment Setup |  |  |  | Team-meeting primarily troubleshooting to get dev environments set up; progress made but still need to sort out starting/connecting back-end server (1.5 hours) Met with Julio from 4:05-4:50 during which we focused on real-time feedback while troubleshooting our collective environment setup and changes/strategies we had employed. More details are contained in the 2/14 notes (0.75 hours) | Backend_Worker successfully running after adjusting dependenices in the apps.js, as well as configuring the versions (1 hour). | Team-meeting. Discussed agenda items (see 2_16_23 Team Meeting Notes); remainder of time spent troubleshooting individual issues with development environment setup. Updated team documents. Exchanged some information with Julio. (1.5 hours) |  | Worked on Backend_Master folder to incorprate with Backend_Worker as Master error reflected what was displayed from Worker folder. (1.5 hours) | Learned the React API to further understand the development/structure of project repo (2 hours). | 6.75
Chris | Local Dev Environment Setup |  |  |  | Team-meeting primarily troubleshooting to get dev environments set up; progress made but still need to sort out starting/connecting back-end server (1.5 hours) Met with Julio from 4:05-4:50 during which we focused on real-time feedback while troubleshooting our collective environment setup and changes/strategies we had employed (50 min). More details are contained in the 2/14 notes (0.75 hours). Having issues still with local setup on computer. Setup on VMware to circumvent possible M1 conflicts (1hr) |  | Team-meeting. Primarily troubleshooting local enviornment issues. (1.5hrs) Continued troubleshooting (1.5hrs) | Downloaded main branch in effort to get local env. working. Frontend would not load / Troubleshoot (1hr) | Continued work on trying to get Master / frontend to load. Compared code from dev and master. Talked to ChatGPT. (2hr) | localhost troubleshooting. reread installation setup. having issues connecting to mongod. website will load but only to blank page still. (2hrs) | 9.75
Elliott | Local Dev Environment Setup |  |  |  | Check-in with the team and housekeeping items - duplicated Figma WFs for modification as Julio directed, compiled questions to ask about connecting to DB (0.5 hours) Pre-meeting collaboration (0.5 hours) Team-meeting primarily troubleshooting to get dev environments set up; progress made but still need to sort out starting/connecting back-end server (1.5 hours) Met with Julio from 4:05-4:50 during which we focused on real-time feedback while troubleshooting our collective environment setup and changes/strategies we had employed. More details are contained in the 2/14 notes (0.75 hours) |  | Team-meeting. Discussed agenda items (see 2_16_23 Team Meeting Notes); remainder of time spent troubleshooting individual issues with development environment setup. Updated team documents. Exchanged some information with Julio. (1.5 hours) Troubleshooting setup continues - compared remote repo branches, compared and attempted to transplant missing directories/files from other working directories (/backend_worker/ contains missing elements referenced by /backend_master/ error logs), researched documentation noted in current error stack traces such as require() and specific modules; attempted fresh setup in master branch (deviates from instructions, unsuccessful - discard changes) (2.5 hours); followed up on Andre's observation, and alongside some questionable and excessive pruning, was successful - more info in Discord checkin (2 hours) | Check-in - formatted notes and thoughts concerning yesterday's progress. May include abbreviated discord logs in sprint deliverables or cite relevant discussions in team meeting notes moving forward. (0.5 hour) Followed Server Setup Guide in PP documentation as suggested in order to confirm local installation of MongoDB is configured properly; WIP (1 hour) |  | Cleaned up local repo as changes were made and confirmed across multiple branches and commits, and formatted my notes documenting troubleshooting steps to improve readability in to receive feedback/clearance from Julio. Also checked in with team regarding our S1 feedback, and updated Team docs, specifically this timesheet, to improve readability per that feedback and 2/16 change that was missed. (.75 hour) | 11.5

## Sprint 2 - Week 2 (220-226)
| Epic | User Story | Status | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | Total Hours
Andre | Local Dev Environment Setup |  |  |  | In-class meeting: had mid-sprint progress check. Project plan may change depending on our progress by Sunday 2/26. Continue documenting any changes. Team meeting - made progress in setup related to MongoDB configuration/installation process. (1.5 hours) Client meeting with Julio - changes we've made thus far seem good - see 2_21_23 Client Meeting Notes for more details (.75 hours)
Chris | Local Dev Environment Setup |  |  | Local env. work. Managed to load webpage. (1.5hrs) | In-class meeting: had mid-sprint progress check. Project plan may change depending on our progress by Sunday 2/26. Continue documenting any changes. Team meeting - made progress in setup related to MongoDB configuration/installation process. (1.5 hours) Client meeting with Julio - changes we've made thus far seem good - see 2_21_23 Client Meeting Notes for more details (.75 hours) Additional work on Mongo connection to PeerPresent. (1hr) - (Total 3.25) |  | mongo setup/troubleshoot (1.5hrs) |  | terminal "killed" trouleshooting(2hrs) | terminal "killed" trouleshooting (3.5hrs) | 11.75
Elliott | Local Dev Environment Setup |  |  |  | In-class meeting: had mid-sprint progress check. Project plan may change depending on our progress by Sunday 2/26. Continue documenting any changes. Team meeting - made progress in setup related to MongoDB configuration/installation process. (1.5 hours) Client meeting with Julio - changes we've made thus far seem good - see 2_21_23 Client Meeting Notes for more details (.75 hours) |  | Met with Andre in-person to work on database issues related to Mongo Shell access and troubleshooting configuration steps listed in https://github.com/Ludolab/PeerPresents/blob/master/docs/admin/server_setup_guide.md Shell can be accessed through mongosh (not mongo) and networking info must match defaults or be parameterized providing a specific ip and port number. Regained access without having to reinstall. (.75 hours) | Successful setup? Looked into database migrations (research) and project code related to db (schema, scripted actions, terminal errors when r/w), comparison between firefox, chrome incompatabilities using respective browser dev tools (DOM includes all elements for both, but does not display certain elements at all in FF and does in Chrome), conveying findings to group specifically step to try chrome after downloading, installing, running compass with connection to 127.0.0.1:27017. Modified mongod.conf file and identified workaround to regain access to mongo shell. Tested to confirm that frontend, storage, and worker were functional and performing CRUD actions in database. Documented steps above and relayed information and current status to the team. (2.25 hours + 1 hour + .75 hour) | Compiled questions for Julio regarding setup - looked into some of the code related to mongo and the schema, read through and researched warning/error logs (frontend not displaying all elements properly in Firefox, mostly correct in Chrome; storage doesn't like the data type for some argument somewhere when reading, possibly other CRUD actions but appears to be functional) Awaiting approval for setup (1 hour) Uploaded and updated documents - meeting notes, timesheet, check-in information (.75 hours) Troubleshooting collaboration: researched system commands "killed" issues for M1/homebrew (1 hour) • possibly $PATH incorrect ◦ try modifying .zsh files (.zshrc and/or .zlogin/.zprofile if you can find the /path/to/relevant/locations) • permissions need to be modified /to/some/locations • possibly boot in safe mode to regain access to shell broken shell commands • unfortunately uninstall/reinstall of homebrew and packages installed through brew • caution with sudo? it works differently* on mac? "doesn't provide full access" • homebrew installations use symlinks so $PATH needs to be set correctly Troubleshooting collaboration: mongod service through homebrew - mongo shell specifically (2 hours) • how to kill and restart if brew services isn't working correctly • confirmed installation via most current method https://github.com/mongodb/homebrew-brew (brew tap?) • compared permissions between linux/mac + version for mongod • possibly bypass shell entirely with using mongo compass (gui) • general research in discussions about homebrew + mongodb compatibility | Sunday tasks (1.25 hours) • replied to julio's post about live db access, e-mail for instructor code • tested remote login/access to production db (account creation works, see class data); awaiting e-mail with instructor code and more information about development and database (use production db? copy it locally? seed data?) • looked into installation problems for mongodb (and homebrew in general) on mac and wrote up a bit more in the team discord about the every process/command killed issue and how to proceed: if troubleshooting current installation, more information from error logs and alternatively a fresh, manual install • bookmarked a few relevant resources and offered to share those Sunday cont.'d (3.25 hours) • Continued troubleshooting killed issue with the team; exploring various potential causes and possible solutions: ◦ identified likely cause/series of commands that led up to it by checking logs (through console) and command history (via history -> .zsh_history) to identify copying /usr/bin/* to /usr/local/bin/ and creating a symlink - problem might be ownership of the copied directory and files, or possibly symlink was created in an unintended location ◦ went through $PATH variable and identified a couple of quirks such as duplicate /usr/local/bin and old versions of mongo (though those don't seem likely culprets for killed issue) ◦ Spent time exploring various paths and their contents ◦ Identified key difference between intel and ARM macs which helped to identify /usr/local/ as a potential problem since homebrew installs to /opt/homebrew/ instead in M1+ • Drafted status e-mail requested by client | 14.75

## Sprint 2 - Week 3 (227-35)
| Epic | User Story | Status | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | Total Hours
Andre | Local Dev Environment Setup |  |  |  | team meeting - discussed sprint 2 demo /sprint 2 reflections / local setup troubleshooting. (1.5 hrs) Client meeting with Julio. Progress check and plans for over spring break. (.5 hrs) |  | Met with Elliott to discuss and prepare our S2 presentation for Demo Day (.75 hours) Met in-person with team following demonstrations to complete our S2 reflection meeting (.5 hours)
Chris | Local Dev Environment Setup |  |  | terminal "killed" trouleshooting(1hrs) | team meeting - discussed sprint 2 demo /sprint 2 reflections / local setup troubleshooting. (1.5 hrs) Client meeting with Julio. Progress check and plans for over spring break. (.5 hrs) terminal "killed" trouleshooting(1hr) | local enviorment setup (1hr) | Met in-person with team following demonstrations to complete our S2 reflection meeting (.5 hours) |  |  |  | 11.75
Elliott | Local Dev Environment Setup |  |  |  | team meeting - discussed sprint 2 demo /sprint 2 reflections / local setup troubleshooting. (1.5 hrs) Client meeting with Julio. Progress check and plans for over spring break. (.5 hrs) | Individual section S2 Reflection, survey + STARFISH responses (2 hours) Drafting human-readable local development environment setup notes/instructions; WIP (2 hours) | Notes doc based on recommended presentation format and looked into M1 (ARM) compatible Linux installation (Asahi & a community-supported alpha Ubuntu build) with the latter being unnecessary as Chris also has access to other architecture (1 hour) Met with Andre to discuss and prepare our S2 presentation for Demo Day (.75 hours) Met in-person with team following demonstrations to complete our S2 reflection meeting (.5 hours) Updated documents/deliverables, committed and pushed to repo, updated README.md to reflect additional information (.75 hours) |  |  |  | 9

## Sprint 1
| Epic | User Story | Status | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19
Andre |  |  |  | Preliminary team meeting: introductions, completed contract (1.5 hours) | First meeting with client + in-class group session (1.5 hours)
Chris |  |  |  | Preliminary team meeting: introductions, completed contract (1.5 hours) | First meeting with client + in-class group session (1.5 hours) | worked on react setup(node), local development setup/troubleshooting same issue with npm install on frontend (3 hrs) | in class coordinating/troubleshooting npm issues (2.5 hrs) |  | Tried to troubleshoot setting up local environment issues (2hrs) | Cont. working on setting up local enviornment(1:45) | local envior. setup troubleshooting. setup project in VM. Client meeting. 3hrs
Elliott |  |  |  | Preliminary team meeting: introductions, completed contract (1.5 hours) | First meeting with client + in-class group session (1.5 hours) | Local Development Environment setup and troubleshooting; ongoing issue with npm install for the frontend, otherwise mostly successful (2.5 hours) | Troubleshooting Dev Environment Setup (Focus was resolving mismatched dependencies), Continued in-class coordinating Sprint 1 deliverables with group (2.0 + 1.5 = 3.5 hours) |  | Troubleshooting dev environment setup. Modified /frontend/src/package.json per notes in the team discord, and was able to start the server locally. Database still refuses connection, but everything seems to be working pending approval for changes made. Communicated the above with team. (1.5 hours)

## Template
| Epic | User Story | Status | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06
Teammate 1 | Register for League | As a player, I can pay with Paypal when I register online | Active | finish task 1 (3 hours) | Finish Task 1, start task 2 & 3 (2 hours) |  | Finish task 2 (1.5 hours) | finish task 3 | attend team meeting (.5 hour)
Teammate 3 | Register for League | As a player, I can pay with Paypal when I register online | Active | [5 empty] | finish task 3 ( 2 hours)
Teammate 2 | Register for League | As a player, I can add league dates to my calendar after I register | Backlog | [6 empty] | start?
Teammate 2 | Register for League | As a league coordinator, I can create a registration survey | Complete | start task 1 | start task 1 (2.5 hours) | finish task 1 (3 hours) | finish task 1 part A (1 hour) |  | finish task 1 part B, attend team meeting (2.5 hours)
Teammate 3 | Register for League | As a captain, I can view all responses to a league signup | Active |  | research how to do task 1 (1.5 hours)

## Blank
| Epic | User Story | Status | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | Total Hours
Andre
Chris
Elliott